## Sheet1
Task | Platform | Assignee | Estimated Difficulty | Status
Change rental status to a SQL ENUM. | SQL | All |  | Done
Add shipping address to rentals. | Desktop | All | Easy, no changes necessary if we allow nulls. | Done / Already there
Restructure project layout to unify all projects under one directory. [see consolidation branch] | All | All/Brandon | Very Difficult! Lots of Nuget errors. | In Progress???
Reflect rental changes. | Desktop | Brandon | Easy? | Done
Allow managers to view rentals sent/received by a specific employee. | Desktop | Brandon | Medium, new UI.
Change desktop UI close the current from when opening a new one. | Desktop | Brandon | Easy? | Done
Have logout button close the current form and open the login form. | Desktop | Brandon | Easy? | Done
Have closing a form using the X button close the program. | Desktop | Brandon | Easy? | Done
Look into removing unneeded columns from viewing items. | Desktop | Brandon | Difficult? | Done
Look into removing unneeded columns from viewing rentals. | Desktop | Brandon | Difficult? | Done
Remove ID from add employee and swap to auto increment value. | Desktop | Brandon | Easy? | Done
Add confirmation for removing an employee on the desktop. | Desktop | Brandon | Medium? | Done
Filter rentals by their status on desktop. | Desktop | Brandon | Medium? | Done
Swap to using stored procedure for adding new employees. | Desktop | Brandon | Easy? | Done
Unit testing. | Desktop | Brandon | Difficult, will have to pull code into controllers to test. | No changes.
Allow managers to view rentals sent/received by a specific employee. | Warehouse Web | Caleb | Medium, some SQL changes might have to be made
Reflect rental changes. | Warehouse Web | Caleb | Already done before | Done
Fix logging in on the web. | Warehouse Web | Caleb | Very Difficult, start early | Done
Fix pages requiring a login to authenticate | Warehouse Web | Caleb | Medium - Difficult | Done
Password requirements on web. | Warehouse Web | Caleb | Easy | Done
Unit testing. | Warehouse Web | Caleb | Medium to difficult, learning ASP ways
Add table for tracking employee ships | All/SQL | Daniel |  | Done
Repurpose ItemReturns for tracking employee returns | All/SQL | Daniel |  | Done
Reflect rental changes. | Member Web | Daniel | Easy | Done
Fix checking out not going to a default user. | Member Web | Daniel | Easy | Done
Allow members to search by name AND type | Member Web | Daniel | Difficult, tricky SQL | Done
Add registration page on the web | Member Web | Daniel | Very Difficult, start early | Done
Fix logging in on the web. | Member Web | Daniel | Very Difficult, start early | Done
Fix pages requiring a login to authenticate | Member Web | Daniel | Medium, ASP trickery | Done
Add a page for members to view their rental history. | Member Web | Daniel | Medium, lot of designing | Done
Add a page for members to view their profile. | Member Web | Daniel | Medium, lot of designing | Done
Restrict members to borrowing only 3 items at once | Member Web | Daniel | Medium, trying to keep controllers simplistic | Done
Allow members to return items marked as Rented (they mark as WaitingReturn) | Member Web | Daniel | Medium, lot of SQL and designing | Done
Unit testing. | Member Web | Daniel | Medium to difficult, learning ASP ways | Session Mocking holding up most tests