## Sheet1
Task | Platform | Assignee | Status | Estimate (hrs)
Removed the Rented status from the ItemRental status enum (WaitingShipment, WaitingReturn, Returned) | SQL | All | Done | 1
Add information for Addresses | SQL | All | Done | 2
Add columns for ItemRental | SQL | All | Done | 2
Allow managers to view records of items tracked by employees | Desktop | Brandon | Done | 5 | Brandon
Add user interface for viewing the history of an employee. | Desktop | Brandon | Done | 2 | 51
Implement controller functionality for viewing the history of an employee. | Desktop | Brandon | Done | 2
Complete any missing documentation (if there is any). | Desktop | Brandon | Done | 1
Refactor TryToLogin into a controller for LoginForm. | Desktop | Brandon | Done | 3
Make changes to rental page to reflect the removal of the Rented status. | Desktop | Brandon | Done | 1
Allow an employee to view the history of a stock item. (returns/in progress) | Desktop | Brandon | Done | 5
Add user interface for viewing the history of a stock item. | Desktop | Brandon | Done | 2
Add controller functionality for viewing the history of a stock item. | Desktop | Brandon | Done | 3
Change "Default" in rental view to "All" | Desktop | Brandon | Done | 1
Unify column / table structure with the website | Desktop | Brandon | Done | 2
Add item name to the display of rentals | Desktop | Brandon | Done | 4
Unit test refactored controller functionality with at least 90% code coverage. (ideally 100%) | Desktop | Brandon | Incomplete | 5
Update class diagram using proper notation. | Desktop | Brandon | Done | 2
Hide unwanted columns in ManageEmployeeForm | Desktop | Brandon | Done | 1
Create Database view for detailed rental information. | SQL | Brandon | Done | 2
Update Controllers to reflect the new Database View. | Desktop | Brandon | Done | 1
Convert RentalDetailForm to use the new Databse View | Desktop | Brandon | Done | 3
Mark updated rentals with the employee who did the action and when the action was made. | Desktop | Brandon | Done | 1
Add view for getting the detailed information on a stock item. | SQL | Brandon | Done | 1
Update ManageItemsForm on desktop to use new View. | Desktop | Brandon | Done | 3
Unify column / table structure with the desktop | Warehouse Web/ Desktop | Brandon/Caleb | Done | 1 | Caleb
Update display for rentals to work with new address table. | Warehouse Web | Caleb | Done | 2 | 47
Allow managers to view records of items tracked by employees | Warehouse Web | Caleb | Done | 3
Add user interface for viewing the history of an employee. | Warehouse Web | Caleb | Done | 2
Add ability to sort employee and item history by date | Warehouse Web | Caleb | Done | 4
Allow an employee to view the history of a stock item. (returns/in progress) | Warehouse Web | Caleb | Done | 3
Add user interface for viewing the history of a stock item. | Warehouse Web | Caleb | Done | 2
Implement controller functionality for viewing the history of a stock item. | Warehouse Web | Caleb | Done | 4
Show employee/item/rental ID's. | Warehouse Web | Caleb | Done | 2
Filter by Rental Status | Warehouse Web | Caleb | Incomplete | 5
Add tests that bring controller coverage to at least 90% | Warehouse Web | Caleb | Done | 10
Update documentation to appropriate levels of verbosity and descriptiveness. | Warehouse Web | Caleb | Done | 3
Update class diagram using proper notation. | Warehouse Web | Caleb | Done | 4
Mark updated rentals with the employee who did the action and when the action was made. | Warehouse Web | Caleb | Done | 2
Update use case scenarios. | All | Caleb | Done | 1
Allow members to store multiple addresses | Member Web | Daniel | Done | 5 | Daniel
Radio buttons should stay selected after a search on the media library. | Member Web | Daniel | Done | 2 | 51
Add a "Clear/Show All" button to searching the media library. | Member Web | Daniel | Done | 2
Order confirmation screen for member to select address when ordering | Member Web | Daniel | Done | 6
Allow members to add address on the order confirmation screen | Member Web | Daniel | Done | 5
Address Create from order confirmation should redirect back to the confirmation screen | Member Web | Daniel | Done | 2
Address Edit from order confirmation should redirect back to the confirmation screen | Member Web | Daniel | Done | 2
Combine user profile and rental history under one page. | Member Web | Daniel | Done | 4
Remove home, about, contact, Need: Login/Register/Library/MemberProfile/EditProfile/OrderConfirmation pages | Member Web | Daniel | Done | 1
Major redirects (logging in, home, logging out) should go to the Login page or Media Library | Member Web | Daniel | Done | 1
Add detailed view of products for members to view | Member Web | Daniel | Done | 3
Add tests that bring test coverage of model items to at least 90%. | Member Web | Daniel | Done | 2
Add tests that bring controller coverage to at least 90% | Member Web | Daniel | Done | 8
Create Session Mock object | Member Web | Daniel | Done | 3
Update documentation to appropriate levels of verbosity and descriptiveness. | Member Web | Daniel | Done | 2
Update class diagram using proper notation. | Member Web | Daniel | Done | 2
Update ER Diagram for database | SQL | Daniel | Done | 1