## Sheet1
Task | Platform | Assignee | Estimated Difficulty | Status
Add shipping address to rentals. | All/SQL | All | Easy, no changes necessary if we allow nulls.
Add employee who ships and returns items to rentals. | All/SQL | All | Medium, will have to repopulate data.
Change rental status to a SQL ENUM. | SQL | All | Medium, will have to repopulate data.
Add static encryption method to database for logging in and creating new members/employees. | Database | Any | Easy
Build static get employee by id and password inside database project if swapped to new encryption. | Database | Any | Medium, would require refactoring.
Change desktop UI close the current from when opening a new one. | Desktop | Brandon | Easy?
Have logout button close the current form and open the login form. | Desktop | Brandon | Easy?
Have closing a form using the X button close the program. | Desktop | Brandon | Easy?
Allow managers to view rentals sent/received by a specific employee. | Desktop | Brandon | Medium, mostly refactoring.
Reflect rental changes. | Desktop | Brandon | Easy?
Look into removing unneeded columns from viewing items. | Desktop | Brandon | Difficult?
Look into removing unneeded columns from viewing rentals. | Desktop | Brandon | Difficult?
Remove ID from add employee and swap to auto increment value. | Desktop | Brandon | Easy?
Unit testing. | Desktop | Brandon | Difficult, will have to pull code into controllers to test.
Swap to DbContext Add if encryption method is added. | Desktop | Brandon | Easy
Allow managers to view rentals sent/received by a specific employee. | Warehouse Web | Caleb | Medium, some SQL changes might have to be made
Fix logging in on the web. | Warehouse Web | Caleb | Very Difficult, start early
Reflect rental changes. | Warehouse Web | Caleb
Unit testing. | Warehouse Web | Caleb | Medium to difficult, learning ASP ways
Password requirements on web. | Warehouse Web | Caleb | Easy
Add librarian login. (checking boolean flag). | Member Web | Caleb / Daniel | Easy - Medium / Might need a procedure or to rework HomeController
Add librarian homepage. | Member Web | Caleb / Daniel | Medium - Designing
Swap to DbContext Add if encryption method is added. | Warehouse Web | Caleb / Daniel | Easy
Restrict members to borrowing only 3 items at once | Member Web | Daniel | Easy, Procedure is done for this
Add a page for members to view their rental history. | Member Web | Daniel | Medium, Procedure mostly in place, but new page needed
Add a page for members to view their profile. | Member Web | Daniel | Medium, lot of designing
Fix logging in on the web. | Member Web | Daniel | Very Difficult, start early
Fix checking out not going to a default user. | Member Web | Daniel | Easy
Reflect rental changes. | Member Web | Daniel | Easy
Unit testing. | Member Web | Daniel | Medium to difficult, learning ASP ways