## Sheet1
Task | Platform | Assignee | Status
Implement warehouse updating an item as sent | Desktop | Brandon | Done
Implement warehouse updating an item as returned | Desktop | Brandon | Done
Allow managers to remove employees | Desktop | Brandon | Done
Implement password criteria on desktop. | Desktop | Brandon | Done
Show password criteria when adding employees. | Desktop | Brandon | Done
Implement Login form vanishing when logged in. | Desktop | Brandon | Done
Implement Viewing Items on Desktop | Desktop | Brandon | Done
Implement database in its own project. | Database | Brandon/Daniel | Done
Implement warehouse seeing items to send | Web | Caleb | Done
Implement warehouse seeing items to receive | Web | Caleb | Done
Allow managers to remove employees | Web | Caleb | Done
Allow managers to add employees | Web | Caleb | Done
Implement warehouse updating an item as sent | Web | Caleb | Done
Implement warehouse updating an item as returned | Web | Caleb | Done
Allow members to borrow new items | Web | Daniel | Done
Moving Database to PhpMyAdmin | Web | Daniel | Done
Restrict members to borrowing only 3 items at once | Web | Daniel | SQL Procedure completed, will need login finished to complete
Allow warehouse to see where orders ship to | Web | Daniel | Done
Show members at password creation the criteria | Web | Daniel | Done