## Sheet1
Task | Platform | Assignee | Status | Estimate (hrs) | Totals
Unit test refactored controller functionality with at least 90% code coverage. (ideally 100%) | Desktop | Brandon | Done | 8 | 34
Create Interface for Database functionality. | Desktop | Brandon | Done | 1
Create class implementing Interface fucntionality. (two constructors) | Desktop | Brandon | Done | 3
Unit test what can be tested in the new class. | Desktop | Brandon | Done | 6
Add ability for managers to remove stock. | Desktop | Brandon | Done | 3
Add ability for managers to add stock. | Desktop | Brandon | Done | 3
Refactor controllers to make use of the new class in a testable way. | Desktop | Brandon | Done | 6
Fix updating rentals. | Desktop | Brandon | Done | 2
Refactor employee history to show rental action first. | Desktop | Brandon | Done | 2
Refactor employee history to show actions first | Warehouse Web | Caleb | Done | 3 | 29
Filter by Rental Status | Warehouse Web | Caleb | Done | 3
Improve documentation | Warehouse Web | Caleb | Done | 3
Allow manangers to add stock | Warehouse Web | Caleb | Done | 4
Allow manangers to remove stock | Warehouse Web | Caleb | Done | 4
Allow flagging of damaged goods | Warehouse Web | Caleb | Done | 4
Add more unit testing | Warehouse Web | Caleb | Done | 6
Refactor | Warehouse Web | Caleb | Done | 2
Allow Librarians to log into the Member Site | Member Web | Daniel | Done | 5 | 30
Properly check authentication of Member OR Librarian across website | Member Web | Daniel | Done | 2
Allow Librarians to view List of all Members | Member Web | Daniel | Done | 2
Allow Librarians to view a members profile | Member Web | Daniel | Done | 2
Allow Librarians to view a members rental history | Member Web | Daniel | Done | 4
Allow Librarians to view a members saved addresses | Member Web | Daniel | Done | 1
Update Topbar Layout to show Member List for Librarians | Member Web | Daniel | Done | 1
Librarians should not be able to rent | Member Web | Daniel | Done | 1
Librarians should not be able to edit information from a Member's Profile *** | Member Web | Daniel | Done | 2
Librarians should not show in All Members table | Member Web | Daniel | Done | 1
Librarians should not be able to see passwords or isLibrarian | Member Web | Daniel | Done | 1
Available Items should filter out unusable stock as well | Member Web | Daniel | Done | 2
Update Unit Testing for new Controller behavior | Member Web | Daniel | Done | 6