## Sheet1
Task | Platform | Assignee | Status
Create desktop login page | Desktop | Brandon | Done
Create page for adding new employees | Desktop | Brandon | Done
Implement database for registering. | SQL Server | Brandon | Done
Create page for managers to see and manage employees. | Desktop | Brandon | Done
Create page for adding employees. | Desktop | Brandon | Done
Implement SQL for login. | Desktop | Brandon | Done
Implement SQL for adding employees. | Desktop | Brandon | Done
Implement SQL for viewing employees | Desktop | Brandon | Done
Create model class for employees. | Desktop/Web | Brandon/Daniel | Done
Create page for browing available items. | Web | Caleb | Done
Create homepage for members | Web | Caleb | Done
Implement SQL for login. | Web | Caleb | Done
Implement databse for items. | SQL Server | Caleb | Done
Implement model class for storing available items. | Desktop/Web | Caleb | Done
Implement database for model members. | SQL Server | Caleb | Done
Create model class for members. | Web | Caleb/Daniel | Done
Implement searching available items in model. | Web | Daniel | Done
Create member login page (also logs in librarians). | Web | Daniel | Done
Create member registration | Web | Daniel | Done
Implement SQL for login. | Warehouse | Daniel | Done
Implement model interface/superclass for items. | Desktop/Web | Daniel | Done
Remove the Warehouse Employee Management Page | Web | Daniel | Done
Create wireframe for website. | Web | Everyone | Done
Create wireframe for desktop. | Desktop | Everyone | Done
Design database for application. | SQL Server | Everyone | Done
Implement model class for fetching items from database. | Web | Everyone | Done